## Sheet2
Product Area | KT Owner (India) | Receiving PM (US/India) | KT Status - NA -Not Required -In process -Not started -Completed | Readiness Score | Target date | Pending Items | Risks Example: “Districts in Texas strongly resist workflow X” “Customer ABC escalates directly to VP” “State release freezes begin 2 weeks before testing” | KT Comments | KT Artifacts ( confluence/ recordings/ etc) | State Walkthrough Done | Shadowing Done | Reverse Demo Done | Receiver Signoff | Validation - Shadow customer calls Run Customer calls Review roadmap and incoming issues independently | Last working day for India Product as of May 13
MA | Chhaya | Turab/NewHire | USKT | 100 |  |  | SIF Unity parallel coming up. | SIF Unity tickets created. Chhaya is part of all calls with customer and handling tickets. | [6 empty] | 2026-12-31
MI Ed-Fi | NA | Turab/NewHire | Not Required | 100 | [10 empty] | 2026-12-31
MN Ed-Fi | NA | Turab/NewHire | USKT | 100 | [10 empty] | 2026-12-31
BC | NA | Shereen | Not Required | 100 | [10 empty] | 2026-12-31
AB | Tehzeeb | Jessica | Not Required | 100 |  | Conformance , Current backlog, Engineering meetings |  | UG & UAT Calls handled by Jessica | [6 empty] | None
KS | Chintan | Jason | In process | 100 |  | None |  | Jason knows the state and customers. |  | Yes | Yes |  |  | Jason leading calls | 2026-12-31
SK | NA | Shereen | Not Required | 100 | [10 empty] | 2026-12-31
NJ | Alka | ShanNita | Not Required | 100 |  |  | Shannita handles all customer intercations | [6 empty] | NA | 2026-12-31
WI Ed-Fi | NA | Turab/NewHire | USKT | 100 | [10 empty] | 2026-12-31
WY | NA / Turab | Jason | Completed | 100 | May | None |  | Turab-Jason |  | Yes | Yes |  |  | Jason in all state calls. | 2026-12-31
GA | Prabha | Vette | Not Required | 90 |  | Current Backlog, Engineering meeting scheduling |  | NA | NA | NA | NA |  |  | Vette leads all calls | 2026-12-31
MO | Anuj/ Jessica | Jessica / Turab | Not Required | 100 |  | None |  | Jessica and Turab are involved in the state from the beginning. KT not required. | [6 empty] | 2026-06-12
CEDS | Soumya | Ben | Continues | NA | [10 empty] | None
MB | NA | Shereen | Not Required | 100 | [10 empty] | 2026-12-31
SIF, SIF Unity | Soumya | Ben | Continues | NA | [10 empty] | None
VA | Alka | ShanNita | Not Required | 100 |  | Current Backlog, Engineering meeting scheduling | Shannita handles all customer intercations | [7 empty] | 2026-12-31
NM | NA | Eric ->Michael | USKT | 100 |  | Eric -> Micheal | [8 empty] | 2026-12-31
OK | Anuj /Turab | Prisana Shaw | USKT | 100 |  | None |  | Jessica and Turab are involved in the state from the beginning. KT not required. | [6 empty] | 2026-06-12
VT | Ajish | Vette/Regina | Not started | 0 |  | Not started | [8 empty] | 2026-12-31
PA | Alka | ShanNita | Not Required | 100 |  | Current Backlog, Engineering meeting scheduling | Shannita handles all customer intercations | [7 empty] | 2026-12-31
ID | Soumya | Michael | Completed | 100 |  |  | None |  | No | No | No | No | No | No | None
UDC | Tehzeeb | NA | Continues | NA |  | Not planned | [8 empty] | None
TX(esp) | Rajesh (eSP) | Fred | Completed | 100 | [10 empty] | 2026-07-03
UT | Soumya | Michael | Completed | 100 |  |  | Utah backpack live date is end of May and is at risk |  | No | No | yes | No | No | No | None
MS | Anuj/Jessica | Caron | USKT | 100 |  |  |  | Jessica and Turab are involved in the state from the beginning. KT not required. | [6 empty] | 2026-06-12
ON | NA | Shereen | Not Required | 100 | [10 empty] | 2026-12-31
MD | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
MN | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
ME | Alka | ShanNita | Not Required | 100 |  |  | Shannita handles all customer intercations | [7 empty] | 2026-12-31
IA | Ankit | Prisana Shaw | Not started | 0 |  | Sif Unity, IA current backlog and future commitments | Sif Unity yearcoming up. | Not required | Not required | Not required | Not required |  |  | Fred is involved in all calls | 2026-12-31
ND | Ankit | Fred | Not Required | LOST |  |  | End of support from June -26 | Not required | Not required | Not required | Not required |  |  | Fred is involved in all calls | 2026-12-31
MT | Chintan | Michael | In process | 100 | [10 empty] | 2026-12-31
FL (esp ) | Himanshu |  | Not started | 0 | [10 empty] | 2026-12-31
NY | Himanshu | Regina | Not started | 0 |  |  | No plan | [7 empty] | 2026-12-31
CA(esp) | Rohan (eSP) | Prashu | Completed | 100 |  |  |  | 1 ticket ongoing communcaiton with customer. To be clarified with customers |  | Done | Done |  | Done | Prashu will lead customer calls from June | 2026-12-31
MD(esp) | Rajesh (eSP) | Prashu | Completed | 100 |  |  |  | done |  | NA | NA |  | Done | From June | 2026-07-03
NJ(esp) | Rajesh (eSP) | Prashu | Completed | 100 |  |  |  | No KT required, Prashu is already taking care of this |  | NA | NA |  | Done | Prashu is handling from March | 2026-07-03
NY | Rohan (eSP) | Prashu | Completed | 100 |  |  |  | Done |  | Done | Done |  | Done | Prashu will lead customer calls from June | 2026-12-31
OR | Rohan (eSP) | Prashu | Completed | 100 | [10 empty] | 2026-12-31
PA | Rajesh (eSP) | Fred | Not Required | 100 |  |  |  | done |  | NA | NA |  | Done | Fred is involved in all calls | 2026-07-03
CRDC | Rohan (eSP) | Prashu | Not started | 0 | [10 empty] | 2026-12-31
IL(esp) | Rohan (eSP) | New Hire | Not started | 100 | [10 empty] | 2026-12-31
MA(esp) | Rohan (eSP) |  | Not Applicable (GONE) | LOST | [10 empty] | 2026-12-31
OH(esp) | Rohan (eSP) | Prashu | Not started | 0 | [10 empty] | 2026-12-31
VA(esp) | Rohan (eSP) | Prashu | Not started | 0 | [10 empty] | 2026-12-31
WA(esp) | Rohan (eSP) | Prashu | Not Required | 0 |  | Only till June 26 | [8 empty] | 2026-12-31
LA | Sivaprasad | Caron | In process | 100 |  |  | None | None | None | None | No | No | No |  | 2026-12-31
WA | Sivaprasad | Dan | Completed | 100 | 2026-06-01 |  | None |  | None | Done | Done | Done |  | Dan leading the calls | 2026-12-31
CO | Smitha | Jason | Completed | 100 | 2026-06-01 |  |  | Completed handover. FG meetings handled by US PM |  | Done | Done | Done |  | Jason leading calls | 2026-12-31
CT | Tehzeeb | Jessica | Completed | 100 |  |  |  | FG & UG Calls handled by Jessica | N/A | N/A |  |  |  |  | None
IL | Tehzeeb | Robyn | Not started | 0 |  | Not planned | [8 empty] | None
OR | Prashu | Dan | Completed | 100 | [5 empty] | Done | Done |  |  | Dan leading the calls
AK | Alka | Dan | Completed | 100 | May |  | Dan handles all customer intercations |  | AK KT Confluence | Done | Done |  |  |  | 2026-12-31
MI | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
NH | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
OH | NA | Meta | Not Required | 100 | [10 empty] | 2026-12-31
RI | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
WI | NA | MBA | Not Required | 100 | [10 empty] | 2026-12-31
AZ | Prashu | Dan | Completed | 100 |  |  |  |  | https://powerschoolgroup.atlassian.net/wiki/spaces/SR/pages/68050452647/Arizona+Product+-+KT | Done | Done |  |  | Dan leading the calls
IN | Himanshu | Caron | In process | 100 |  |  | Caron will start running the calls from Aug. |  | https://powerschoolgroup.atlassian.net/wiki/spaces/SR/pages/68179034174/Indiana+State+Reporting+Product+Management+Knowledge+Transfer+Overview | [5 empty] | 2026-12-31
NE | Chintan | Prisana Shaw | Not started | 0 |  | KT not started | [8 empty] | 2026-12-31
CA | Sivaprasad | Jason | Completed | 100 |  | Day to Day Backlog management and sprint planning. Customer Introduction | None | N/A | CA Transition Document | Yes | No | No | No | Jason leading calls | 2026-12-31
AL | Smitha | Debra | Not Required | 80 |  | Current Backlog, Engineering meeting scheduling |  |  |  | NA | NA |  |  |  | 2026-12-31
FL (SIS) | Himanshu | Debra | Not Required | NA |  | Closure meeting with current / pending backlog | [8 empty] | 2026-12-31
SC | Ajish | Vette | Not Required | 90 |  | Current Backlog, Engineering meeting scheduling |  | Not required | Not required | Not required | Not required |  |  | Vette leads all meetings | 2026-12-31
TN | Ajish | Vette | Not Required | 90 |  | Current Backlog, Engineering meeting scheduling |  | Not required | Not required | Not required | Not required |  |  | Vette leads all meetings | 2026-12-31
TX | Ankit | Fred | Not Required | 80 |  | Current Backlog, Engineering meeting scheduling | 26-27 Requirements | Not required | Not required | Not required | Not required |  |  | Fred is involved in all calls | 2026-12-31
Ed-fi, DEX | Soumya | Ben | Continues | NA | [10 empty] | None
Note on A32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Last year of support
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Last year of support

## Q3 status
State / Product Area | KT Owner (India) | Receiving PM (US/India) | KT Status - NA -Not Required -In process -Not started -Completed | Readiness Score - kt | Grooming | Demos | New requirements/tickets | Customer slides | Customer calls | Release notes | Dev clarifications | Bugs / support calls | Customer calls for new reqs. | US PM Vacation/ Conference support
MA | Chhaya | Turab/NewHire | USKT | 100 | 30 | 30 | 0 | 30 | 30 | 50 | 30 | 0 | 0 | 100
MI Ed-Fi | NA | Turab/NewHire | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
MN Ed-Fi | NA | Turab/NewHire | USKT | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
BC | NA | Shereen | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
AB | Tehzeeb | Jessica | Not Required | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
KS | Chintan | Jason | In process | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
SK | NA | Shereen | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
NJ | Alka | ShanNita | Not Required | 100 | 80 | 50 | 0 | 0 | 20 | 100 | 80 | 50 | 0 | 100
WI Ed-Fi | NA | Turab/NewHire | USKT | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
WY | NA / Turab | Jason | Completed | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
GA | Prabha | Vette | Not Required | 90 | 80 | 80 | 50 | 0 | 30 | 100 | 100 | 30 | 20 | 100
MO | Anuj/ Jessica | Jessica / Turab | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
CEDS | Soumya | Ben | Continues | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
MB | NA | Shereen | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
SIF, SIF Unity | Soumya | Ben | Continues | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
VA | Alka | ShanNita | Not Required | 100 | 80 | 50 | 0 | 0 | 20 | 100 | 80 | 50 | 0 | 100
NM | NA | Eric ->Michael | USKT | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
OK | Anuj /Turab | Prisana Shaw | USKT | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
VT | Ajish | Regina | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
PA | Alka | ShanNita | Not Required | 100 | 80 | 50 | 0 | 0 | 20 | 100 | 80 | 50 | 0 | 100
ID | Soumya | Michael | Completed | 100 | 100 | 50 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100
UDC | Tehzeeb | NA | Continues | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
TX(esp) | Rajesh (eSP) | Fred | Completed | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
UT | Soumya | Michael | Completed | 100 | 100 | 50 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100
MS | Anuj/Jessica | Caron | USKT | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
ON | NA | Shereen | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
MD | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
MN | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
ME | Alka | ShanNita | Not Required | 100 | 80 | 50 | 0 | 0 | 0 | 100 | 80 | 50 | 0 | 100
IA | Ankit | Prisana Shaw | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
ND | Ankit | Fred | Not Required | LOST
MT | Chintan | Michael | In process | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
FL (esp ) | Himanshu |  | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
NY | Himanshu | Regina | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
CA(esp) | Rohan (eSP) | Prashu | Completed | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
MD(esp) | Rajesh (eSP) | Prashu | Completed | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
NJ(esp) | Rajesh (eSP) | Prashu | Completed | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
NY | Rohan (eSP) | Prashu | Completed | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
OR | Rohan (eSP) | Prashu | Completed | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
PA | Rajesh (eSP) | Fred | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
CRDC | Rohan (eSP) | Prashu | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
IL(esp) | Rohan (eSP) | New Hire | Not started | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
MA(esp) | Rohan (eSP) |  | Not Applicable (GONE) | LOST
OH(esp) | Rohan (eSP) | Prashu | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
VA(esp) | Rohan (eSP) | Prashu | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
WA(esp) | Rohan (eSP) | Prashu | Not Required | LOST
LA | Sivaprasad | Caron | In process | 100 | 100 | 100 | 100 | 100 | 100 | 50 | 100 | 50 | 80 | 100
WA | Sivaprasad | Dan | Completed | 100 | 100 | 100 | 0 | 0 | 20 | 50 | 50 | 0 | 0 | 100
CO | Smitha | Jason | Completed | 100 | 0 | 100 | 20 | 0 | 0 | 30 | 50 | 0 | 0 | 100
CT | Tehzeeb | Jessica | Completed | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
IL | Tehzeeb | Robyn | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
OR | Prashu | Dan | Completed | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
AK | Alka | Dan | Completed | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
MI | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
NH | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
OH | NA | Meta | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
RI | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
WI | NA | MBA | Not Required | 100 | NA | NA | NA | NA | NA | NA | NA | NA | NA
AZ | Prashu | Dan | Completed | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
IN | Himanshu | Caron | In process | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
NE | Chintan | Prisana Shaw | Not started | 0 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
CA | Sivaprasad | Jason | Completed | 100 | 100 | 100 | 0 | 0 | 20 | 50 | 50 | 0 | 0 | 100
AL | Smitha | Debra | Not Required | 100 | 100 | 100 | 100 | 30 | 50 | 100 | 100 | 100 | 0 | 100
FL (SIS) | Himanshu | Debra | Not Required | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
SC | Ajish | Vette | Not Required | 90 | 100 | 100 | 50 | 0 | 25 | 100 | 50 | 50 | 20 | 100
TN | Ajish | Vette | Not Required | 90 | 100 | 100 | 50 | 0 | 0 | 100 | 50 | 30 | 0 | 100
TX | Ankit | Fred | Not Required | 80 | 100 | 100 | 80 | 80 | 80 | 100 | 100 | 80 | 80 | 100
Ed-fi, DEX | Soumya | Ben | Continues | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Note on A32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Last year of support
Note on A44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Last year of support